## Slide 1
Hands-On Project Design Experience
Operational Setup, Challenges, and Lessons Learned in Agri-Carbon Markets
PDB Perspective – Implementation at Project-Level for
Carbon Projects
A cross-project operations synthesis exploring the technical architectures, key operational realities, and core commonalities across NbS and Biochar pathways.
Presented by: Mr. Aftab Khairdi • National Bank for Agriculture and Rural Development (NABARD)

## Slide 2
Project Design
Rigorous Baseline & Additionality Setup, Leakage, Buffer
Alignment with Methodology
Rigid Carbon & Metric Modelling
Operational Setup
Smallholder Farmer Aggregation
Quality Data Infrastructure
Auditor (VVB) Scrutiny Management
Setting the Foundation
Critical Field Challenges
Complex Sourcing & Legal Verification
Benefit-Sharing Equity Tensions
Extended development cycle
Methodology design
Lessons Learned
De-Jargon the Core Communication
Financial Transparency
Pragmatic Field Compromise

## Slide 3
Months 1 - 4
Feasibility assessments, legal land rights validation, and preliminary stakeholder approvals.
Months 5 - 10
PDD drafting, establishing rigorous baselines, and modeling regional ERR calculations.
Months 11 - 15
Auditor field visits (VVB validation), answering queries, and standard registry submission.
Months 16 - 18+
Formal project registration, initiating regular field MRV, and final credit issuance.
Real-World Project Lifecycle

## Slide 4
18+
MONTHS BEFORE PAYOUTS
Managing Local Expectations
The transition period from initial feasibility to active credit registration typically exceeds 18 months. This lag requires careful, patient community engagement.
Farmers invest initial field labor months before financial offsets are verified.
Continuous communications must bridge the expectation gap.
Sustained PDB support provides critical baseline finance.
•
•
•
The Extended Time Lag

## Slide 5
Transition Pillar Overview
A hands-on review of concrete field experiences deploying ARR, ALM and Biochar solutions across fragmented smallholder farmlands.

## Slide 6
Project Design
Degraded Land Stratification
Standard-Specific Selection
Operational Setup
Plantation Layout & Silviculture
Rainfall Synchronization
ARR Carbon Projects (Afforestation, Reforestation, & Revegetation)
Critical Field Challenges
Undocumented Land Tenure
Lessons Learned
Livelihoods Over Carbon

## Slide 7
Project Design
Agricultural Baseline Modelling
Methane Reduction Architecture
Operational Setup
Smart-Practice Deployment
MRV Infrastructure
ALM Carbon Projects (Agricultural Land Management)
Critical Field Challenges
Fragmented Boundary Data
Lessons Learned
Integrating Traditional Practices

## Slide 8
Project Design
Removal Framework Alignment
Lifecycle Assessment (LCA)
Operational Setup
Pyrolysis System Certification
Value-Stream Engineering through alternate uses
Biochar Carbon Project (Engineered Removal)
Critical Field Challenges
Feedstock Sourcing Infrastructure
High Unit Costs & Subsidies
Lessons Learned
Layered Revenue Engineering by aligning CC with alternative uses

## Slide 9
Strength
Unrivalled Rural Network
Dedicated Climate Infrastructure
Strong network with global and national players
Weakness
High Transaction Costs per Hectare
Historically Risk-Averse Ecosystem
Capacity & Literacy Constraints
A Financial Institutions perspective
Opportunities
Operationalizing the India Carbon Credit Trading Scheme
Untapped sector/ First movers advantage
Achievement of mandate
Threats
Interest servicing
Monsoon and Climate Vulnerability
Intl/ Domestic Regulatory Uncertainty

## Slide 10: Core Takeaway
Credible, high-impact climate mitigation only succeeds when the technical rigor of global carbon standards is fully integrated with the ground-level economic realities of local communities.
Agri-PDB Carbon Credit Webinar

## Slide 11
dcas@nabard.org
www.nabard.com